## Sheet1
Task # | Task Name | Duration | Start Date | Finish Date | Dependency | Resource | Outline Level | % Complete | Task Notes | Actual Start | Actual Finish | Actual Duration | User Defined Number | User Defined Time | User Defined Text 1 | User Defined Text 2 | User Defined Text 3 | User Defined Text 4 | User Defined Text 5 | User Defined Decimal | User Defined Duration
1 | Planing and Research | 0.5 | 2020-02-10 09:00 | 2020-02-10 12:00 |  |  | 1 | 0 |  | 2014-09-09 08:00 |  |  | 0 | 2014-09-09 10:40 | [5 empty] | 0 | 1
2 | Intergrate Rasberry pi | 1.5 | 2020-02-10 14:00 | 2020-02-11 17:00 | 1 |  | 1 | 0 |  | 2014-09-24 08:00 |  |  | 0 | 2014-09-24 10:40 | [5 empty] | 0 | 1
3 | power circuit | 0.5 | 2020-02-10 14:00 | 2020-02-10 17:00 | 1 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
4 | i2c bus intergratrion | 0.5 | 2020-02-11 09:00 | 2020-02-11 12:00 | 3 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
5 | code for motor control | 0.5 | 2020-02-11 14:00 | 2020-02-11 17:00 | 4 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
6 | Utrasonic sensor system | 3 | 2020-02-12 09:00 | 2020-02-14 17:00 | 2 |  | 1 | 0 |  | 2014-10-14 08:00 |  |  | 0 | 2014-10-14 10:40 | [5 empty] | 0 | 1
7 | Mounting and wiring | 0.5 | 2020-02-12 09:00 | 2020-02-12 12:00 | 2 |  | 2 | 0 |  | 2014-10-14 08:00 |  |  | 0 | 2014-10-14 10:40 | [5 empty] | 0 | 1
8 | Interfacing with rasberry pi | 1 | 2020-02-12 12:00 | 2020-02-13 12:00 | 8 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
9 | Display distance on screen | 1 | 2020-02-13 12:00 | 2020-02-14 12:00 | 9 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
10 | Build screen circuit | 0.5 | 2020-02-13 12:00 | 2020-02-13 17:00 | 9 |  | 3 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
11 | Interface rasberry pi with screen | 0.5 | 2020-02-13 17:00 | 2020-02-14 12:00 | 10 |  | 3 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
12 | Speak distance | 0.5 | 2020-02-14 12:00 | 2020-02-14 17:00 | 2 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
13 | text to speech library code | 0.5 | 2020-02-14 12:00 | 2020-02-14 17:00 | 2 |  | 3 | 0 |  | 2014-10-16 08:00 |  |  | 0 | 2014-10-16 10:40 | [5 empty] | 0 | 1
15 | Speaker and amplifyer | 3 | 2020-02-12 09:00 | 2020-02-14 17:00 | 2 |  | 1 | 0 |  | 2014-10-16 08:00 |  |  | 0 | 2014-10-16 10:40 | [5 empty] | 0 | 1
16 | Design amplifyer circuit | 1 | 2020-02-12 09:00 | 2020-02-12 17:00 | 2 |  | 2 | 0 |  | 2014-10-16 08:00 |  |  | 0 | 2014-10-16 10:40 | [5 empty] | 0 | 1
17 | Build amplifyer circuit | 0.5 | 2020-02-13 09:00 | 2020-02-13 12:00 | 16 |  | 2 | 0 |  | 2014-10-21 08:00 |  |  | 0 | 2014-10-21 10:40 | [5 empty] | 0 | 1
18 | Testing | 1 | 2020-02-13 12:00 | 2020-02-14 12:00 | 17 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1
19 | Rasberry pi intergration | 0.5 | 2020-02-14 12:00 | 2020-02-14 17:00 | 19 |  | 2 | 0 |  | 2014-10-29 08:00 |  |  | 0 | 2014-10-29 10:40 | [5 empty] | 0 | 1